## TASKS
TASK LIST CSC 420 Project
MY TASKS | START DATE | DUE DATE | % COMPLETE | DONE | NOTES
Team Organization | 2017-11-01 | 2017-11-03 | 100% | 1 | No team leader - work together on everything
Task List | 2017-11-08 | 2017-11-10 | 100% | 1 | Finalized 11-10
First Checkin | 2017-11-03 | 2017-11-06 | 100% | 1 | Compiler can parse any MountC program
Second Checkin | 2017-11-08 | 2017-11-13 |  | 0 | Compiler can generate correct Pep/9 code for main (with no parameters) and expressions not involving if-expressions nor function calls—other than getint and putint
Third Checkin | 2017-11-08 | 2017-11-20 |  | 0 | Compiler can generate correct Pep/9 code for main and expressions not involving function calls—other than getint and putint
Fourth Checkin | 2017-11-08 | 2017-12-01 |  | 0 | Compiler can generate correct Pep/9 code for any MountC program, including function calls with no parameters
Fifth Checkin |  | 2017-12-08 |  | 0 | Compiler can generate correct Pep/9 code for any MountC program, including function calls with any number of parameters
Assessment Report |  | 2017-12-08 |  | 0 | Done Individually
Meeting Dates: | Members Absent:
2017-10-31 | None
2017-11-03 | Tyler
2017-11-08 | None
2017-11-10 | Tyler